## Open
Risk no/ category | Description (Causal factor) | Controls already in place / Activity undertaken in the last 3 months to reduce/mitigate the risk | Additional action planned | Date raised/ Risk level changed | Likelihood | Impact | Current Rank | Accountable Officer
1 | Council withdraws or further reduces funding for the service. | HWW holds reserves to deal with its contractual finacial obligations in event of this risk occuring. | In event of Council giving notice HWW to engage with Healthwatch England. | 1.04.2019 | Very low | Extreme | 17 [Medium] | JR
2 | Staff resign from HWW due to uncertainty over year 2 funding |  | Response will depend on proximity of event to end of contract | 17.11.2020 | High | Critical | 20 [High] | SA
3 | HWW takes'ulra vires' action'as a local healthwatch/public body/registered company | ISO 9001 accredited governance controls in place. SA appointed Director following JR's additional responssibility as DPO. Review of Directors responsibilities. Periodic review of HWW's risk register. | Periodic review of risk register. Annual assessment to support ISO 9001 accreditation and Cyber Essentails. Annual Report | 1.04.2019 | Very low | Critical | 14 [Medium] | MG
4 | Late contractual payment by WCC | Agreed contract terms between HWW and WCC. Monitoring by HWW. | Letter to WCC in advance of payment due date. | 1.04.2019 | Medium | Critical | 15 [Medium] | JR
5 | Failure of Business Systems. Unable to deliver the service or administer the Company | IT Maintenance contract in place. | Formalise Business Continuity Arrangements | 1.04.2019 | Very low | Sunstantial | 6 [Low] | SA
6 | Sustainability due to financial/HR resouce issues as contract end date approached. | Cost control | HR recruitment plan | 30.10.2019 | Medium | Substantial | 15 {medium} | SA
7 | [7 empty] | MG

## Closed
No. | Description (Causal factor) | Controls Already in Place | Additional Action Planned | Date Raised/ Risk level changed / Closed | Likelihood | Impact | Rank | Accountable Officer | ICEOG | CMB | CQR

## Matrix
Evaluation of Risk – Likelihood and Impact Matrix
Likelihood
Impact